## Worksheet
Project Timeline - Administrative Support
Phase | Task Description | Start Date | End Date | Status | Responsible Team
Planning & Initiation | Define project scope and objectives | 2024-01-05 | 2024-01-15 | In Progress | Project Management Office
Resource Allocation | Assign administrative staff and schedule training | 2024-01-16 | 2024-01-31 | Pending | HR & Admin Team
Data Preparation | Compile and verify all required documentation and records | 2024-02-01 | 2024-02-15 | Pending | Data Entry Team
Process Implementation | Roll out new administrative procedures and workflows | 2024-02-16 | 2024-03-15 | Pending | Operations Team
Monitoring & Review | Track progress and conduct bi-weekly review meetings | 2024-03-16 | 2024-04-30 | Pending | Project Coordinator
Closure & Evaluation | Finalize documentation and conduct project evaluation report | 2024-05-01 | 2024-05-15 | Pending | All Departments