## Worksheet
Project Timeline - Report Version
Task ID | Task Name | Description | Start Date | End Date | Status | Responsible Party
T001 | Project Initiation | Define project scope, objectives, and stakeholders. | 2024-05-15 | 2024-05-18 | In Progress | Jane Smith
T002 | Requirements Gathering | Collect and document detailed project requirements. | 2024-05-19 | 2024-05-31 | Pending | John Doe
T003 | Design Phase | Create system architecture and UI mockups. | 2024-06-01 | 2024-06-15 | Pending | Lisa Chen
T004 | Development Phase (Frontend) | Implement user interface components. | 2024-06-16 | 2024-07-15 | Pending | Mike Johnson
T005 | Development Phase (Backend) | Build server-side logic and database structure. | 2024-06-16 | 2024-07-31 | Pending | Sarah Williams
T006 | Testing & QA | Conduct system testing, bug fixes, and quality assurance. | 2024-08-01 | 2024-08-31 | Pending | Alex Brown
T007 | User Training | Prepare training materials and conduct sessions. | 2024-09-01 | 2024-09-15 | Pending | Jane Smith
T008 | Deployment & Go-Live | Deploy system to production and monitor initial performance. | 2024-09-16 | 2024-09-30 | Pending | Mike Johnson
T009 | Project Closure & Review | Conduct post-mortem, finalize documentation, and close project. | 2024-10-01 | 2024-10-15 | Pending | Jane Smith