## Worksheet
Project Timeline - Administrative Support
Task | Start Date | End Date | Status | Responsible Team/Person
Project Kickoff Meeting | 2023-10-01 | 2023-10-01 | Completed | Project Manager
Document Preparation | 2023-10-02 | 2023-10-05 | In Progress | Admin Team
Data Entry & Verification | 2023-10-06 | 2023-10-10 | Not Started | Data Coordinator
Weekly Status Report Submission | 2023-10-11 | 2023-10-14 | Not Started | Admin Assistant
Milestone Review Meeting | 2023-10-15 | 2023-10-15 | Not Started | Project Manager, Admin Team
Final Documentation & Archiving | 2023-10-16 | 2023-10-18 | Not Started | Admin Team, Supervisor