## Worksheet
Task | Start Date | End Date | Status | Assigned To
Project Initiation | 2023-10-01 | 2023-10-05 | Completed | Jane Smith
Requirements Gathering | 2023-10-06 | 2023-10-15 | In Progress | John Doe
Planning & Scheduling | 2023-10-16 | 2023-10-25 | In Progress | Jane Smith
Resource Allocation | 2023-10-26 | 2023-11-05 | Not Started | Mike Johnson
Milestone Review 1 | 2023-11-06 | 2023-11-08 | Not Started | Jane Smith
Design Phase | 2023-11-09 | 2023-11-25 | Not Started | Alex Brown
Development Start | 2023-11-26 | 2024-01-15 | Not Started | Lisa Wong
Milestone Review 2 | 2024-01-16 | 2024-01-18 | Not Started | Jane Smith
Testing & QA | 2024-01-19 | 2024-02-15 | Not Started | Alex Brown
Deployment Preparation | 2024-02-16 | 2024-03-01 | Not Started | Lisa Wong
Final Deployment | 2024-03-02 | 2024-03-15 | Not Started | Mike Johnson
Project Closure & Review | 2024-03-16 | 2024-03-31 | Not Started | Jane Smith