## Worksheet
Project Timeline - Administrative Support (Team Use)
Task | Start Date | End Date | Status | Assigned To | Priority
Project Kickoff Meeting | 2024-01-05 | 2024-01-05 | Completed | Alice Johnson | High
Create Project Documentation | 2024-01-06 | 2024-01-15 | In Progress | Bob Smith | Moderate
Resource Allocation Planning | 2024-01-16 | 2024-01-20 | Pending | Catherine Lee | Moderate
Draft Budget Proposal | 2024-01-18 | 2024-01-25 | Pending | David Brown | High
Critical Vendor Onboarding | 2024-01-262024-01-31In ProgressMaria GarciaHigh
Milestone Review 1 (Midpoint) | 2024-02-01 | 2024-02-05 | Pending
Final Report Compilation | 2024-02-15 | 2024-02-28 | Pending
Project Closeout Meeting | 2024-03-01 | 2024-03-01 | Pending
All Team MembersLow
Team Use - Administrative Support Project Timeline • Last Updated: June 10, 2024