## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Progress (%)
TSK001 | Project Initiation | Jane Smith | 2024-01-05 | 2024-01-15 | Completed | 100%
TSK002 | Resource Allocation | John Doe | 2024-01-16 | 2024-01-31 | In Progress | 75%
TSK003 | Milestone Planning | Alice Brown | 2024-02-01 | 2024-02-15 | Scheduled | 0%
TSK004 | Weekly Review Meeting | Jane Smith | 2024-02-16 | 2024-03-15 | Scheduled | 0%
TSK005 | Final Report Preparation | John Doe | 2024-03-16 | 2024-04-15 | Scheduled | 0%
Total Tasks: |  |  |  |  | 5
Completed: |  |  |  |  | 1 (20%)