## Worksheet
Week | Task Description | Assigned To | Start Date | End Date | Status
Week 1 | Project Kickoff Meeting & Initial Planning | John Doe | 2024-04-01 | 2024-04-05 | Completed
Week 2 | Develop Project Scope Document | Jane Smith | 2024-04-08 | 2024-04-12 | In Progress
Week 3 | Resource Allocation & Team Assignment | Robert Brown | 2024-04-15 | 2024-04-19 | Pending
Week 4 | Design Phase - Initial Wireframes & Mockups | Sarah Johnson | 2024-04-22 | 2024-04-26 | Not Started
Week 5 | Review & Feedback Session (Design Phase) | John Doe, Jane Smith | 2024-04-29 | 2024-05-03 | Not Started
Week 6 | Development Phase - Frontend Implementation | Mike Wilson | 2024-05-06 | 2024-05-10 | Not Started
Week 7 | Development Phase - Backend Integration | Lisa Garcia | 2024-05-13 | 2024-05-17 | Not Started
Week 8 | Testing Phase - Unit & Integration Testing | Daniel Lee | 2024-05-20 | 2024-05-24 | Not Started
Week 9 | User Acceptance Testing (UAT) | Team & Stakeholders | 2024-05-27 | 2024-05-31 | Not Started
Week 10 | Final Review & Project Handover | John Doe, Jane Smith | 2024-06-03 | 2024-06-07 | Not Started
Total Weeks: |  |  |  |  | 10