## Project Tracker - Analysis View
Project Tracker - Analysis View
Project ID | Project Name | Initiator | Status | Start Date | Target End Date | Actual End Date | Budget (USD) | Spent (USD) | Completion (%) | Risk Level | Notes/Comments
PJ001 | Office Automation Upgrade | Jane Smith | In Progress | 2023-09-15 | 2024-03-31 | - | 50,000.00 | 28,567.42 | 57% | Moderate | Vendor delivery delayed by 2 weeks.
PJ002 | HR Onboarding System Migration | Mark Johnson | On Hold | 2023-11-01 | 2024-05-31 | - | 75,000.00 | 9,876.34 | 13% | Waiting on IT infrastructure approval.
PJ003 | Cybersecurity Compliance Audit | Sarah Lee | Completed | 2023-07-10 | 2023-11-30 | 2023-11-25 | 45,500.00 | 44,987.66 | 100% | No findings reported.
Totals: |  |  | N/A | N/A | N/A | N/A | $170,500.00 | $83,431.42 | ~56% | N/A | N/A