## Worksheet
Annual Project Tracker - Administrative Support
Project ID | Project Name | Description | Start Date | End Date | Status | Budget (USD) | Actual Cost (USD) | Progress (%)
PJ-2024-001 | Office Facility Upgrade | Renovation and modernization of administrative offices | Jan 15, 2024 | Apr 30, 2024 | In Progress | $75,000.00 | $48,956.75 | 65%
PJ-2024-002 | IT System Migration | Migrate legacy systems to cloud-based platform | Mar 1, 2024 | Jun 30, 2024 | In Progress | $150,000.00 | $89,376.54 | 59%
PJ-2024-003 | Staff Training Program | Quarterly professional development sessions for admin team | Jan 1, 2024 | Dec 31, 2024 | On Track | $50,000.00 | $15,689.33 | 31%
PJ-2024-004 | Document Management System Implementation | Deploy new digital filing and retrieval system | Feb 15, 2024 | Aug 15, 2024 | In Progress | $60,000.00 | $34,789.16 | 58%
Total Projects: | [5 empty] | $335,000.00 | $188,811.78 | N/A