## Worksheet
Task ID | Task Description | Assigned To | Status | Priority | Start Date | Due Date | Daily Progress (%)
TASK001 | Prepare meeting agenda for weekly team sync | Jane Doe | In Progress | High | 2025-04-14 | 2025-04-16 | 75%
TASK002 | Update project documentation for Q2 goals | John Smith | Not Started | Medium | 2025-04-14 | 2025-04-18 | 0%
TASK003 | Coordinate travel arrangements for client visit | Sarah Lee | Completed | High | 2025-04-13 | 2025-04-15 | 100%
TASK004 | Review and approve expense reports from team | Mike Brown | In Review | High | 2025-04-15 | 2025-04-16 | 90%
TASK005 | Set up new employee onboarding folder | Lisa Wong | In Progress | Medium | 2025-04-14 | 2025-04-17 | 60%
Total Tasks: | [6 empty] | 5
Notes:
Status options: Not Started, In Progress, In Review, Completed
Priorities: High, Medium, Low
Progress percentages reflect daily updates as of today's date.