## Worksheet
Project Tracker - Administrative Support
Project ID | Project Name | Status | Start Date | End Date | Manager
PJ001 | Office Relocation | In Progress | 2024-01-15 | 2024-03-31 | Jane Smith
PJ002 | Staff Onboarding System Upgrade | Planning | 2024-02-15 | 2024-06-30 | Mike Johnson
PJ003 | Fiscal Year Budget Planning | Completed | 2024-01-15 | 2024-12-31 | Sarah Brown
PJ004 | Facility Maintenance Schedule Update | In Progress | 2024-03-01 | 2024-11-30 | Tony Reed
Project ID | Task Name | Assigned To | Status | Due Date | Progress (%)
PJ001 | Survey Current Office Layouts | Lisa Chen | Completed | 2024-01-25 | 100%
PJ001 | Select New Location Vendor | Jane Smith | In Progress | 2024-03-15 | 65%
PJ002 | Review Current Onboarding Process | Mike Johnson | In Progress | 2024-03-15 | 75%
PJ002 | Select New System Platform | Daniel Lee | Not Started | 2024-04-30 | 15%
Project ID | Resource Type | Name/Description | Assigned Quantity | Budget Allocated ($)
PJ001 | Personnel | Office Move Coordinator | 1 | 5,000.00
PJ001 | Equipment | Furniture and Fixtures (New Office) | 32 units | 48,756.32
PJ002 | Software License | New Onboarding Platform - Annual Subscription | 1 license (unlimited users) | 8,995.00
PJ003 | Consultant Services | Fiscal Planning Advisor (Part-time) | 6 weeks of work | 12,500.00
Project ID | Milestone Name | Planned Date | Status | Actual Date
PJ001 | Finalize New Office Lease Agreement | 2024-02-15 | In Progress
PJ001 | Complete Interior Design Plans Review
PJ002 | System Requirements Document Approved
PJ003 | Fiscal Year Budget Presented to Executive Board
Type | Description | Owner | Due Date
Risk | Potential delay in lease signing due to vendor contract negotiations. | Jane Smith | 2024-03-15
Note
Action Item
Risk