## Worksheet
Quarterly Project Tracker - Administrative Support
Quarter:Q1 2024 ¦Department:Administrative Services ¦Last Updated:April 5, 2024
ID | Project Name | Description | Start Date | Target End Date | Status | Progress (%)
P001 | Office Reorganization Initiative | Restructure office layout for improved workflow and efficiency. | Jan 5, 2024 | Mar 31, 2024 | Completed | 100%
P002 | HR Onboarding Portal Upgrade | Enhance digital onboarding system with automated workflows. | Jan 15, 2024 | Apr 15, 2024 | In Progress | 75%
P003 | Annual Budget Planning Support | Coordinate with departments to collect and analyze budget proposals. | Jan 1, 2024 | Mar 31, 2024 | Completed | 100%
P004 | Facilities Maintenance Schedule Update | Reassess and update facility maintenance calendar for Q2. | Feb 1, 2024 | Mar 31, 2024 | Completed | 100%
P005 | Internal Communication Platform Migration | Migrate from legacy system to modern enterprise messaging platform. | Feb 20, 2024 | May 31, 2024 | In Progress | 65%
P006 | Document Management System Implementation | Deploy new centralized document storage and access system. | Mar 1, 2024 | May 31, 2024 | Pending | 5%
Legend:
Completed
In Progress
Pending