## Worksheet
Weekly Project Tracker - Administrative Support
Week Ending | Project Name | Assigned To | Status | Tasks Completed (This Week) | Next Steps/Goals | Budget Used ($)
2023-10-06 | Office Renovation Planning | Jane Smith | In Progress | Site inspection, vendor list compiled, budget draft completed | Finalize vendor selection and schedule installation dates | 4,250.00
2023-10-06 | Employee Onboarding System Upgrade | Mike Johnson | On Hold | Requirements gathering completed, awaiting approval from HR Director | Pending final sign-off; initiate testing phase upon approval | 1,800.00
2023-10-06 | Quarterly Reporting Package | Sarah Lee | Completed | Data collection, report drafting, review and submission completed | Archive documents and prepare for next quarter's template updates | 650
2023-10-06 | Annual Conference Logistics | David Brown | In Progress | Catering contracts signed, venue secured, registration platform tested | Finalize speaker confirmations and send out invitation emails | 12,500.00
2023-10-06 | IT Equipment Inventory Audit | Lisa Chen | Pending Review | All devices scanned and logged; data validation pending | Review discrepancies and update asset tracking system by Friday | 800
Total Projects: | [5 empty] | 19,550.00