## Audit Preparation Dashboard
Audit Preparation Dashboard
Business Template ¦ Purpose: Audit Preparation ¦ Version: Dashboard View
Audit Summary
Category | Status | Due Date | Responsible Team
Financial Records Review | Pending | 2023-10-15 | Finance Department
Compliance Documentation | Completed | 2023-10-10 | Legal & Compliance
Risk Assessment Report | Pending | 2023-10-20 | Risk Management
Internal Controls Verification | Overdue | 2023-10-05 | Internal Audit
Key Performance Indicators
KPI Metric | Target | Current Value | Status
Document Completeness Rate | 100% | 92% | On Track
Audit Readiness Score | 95% | 87% | Needs Attention
Issue Resolution Rate | 100% | 84% | On Track
Team Task Completion | 95% | 90% | On Track
Action Items & Follow-ups
Action Item | Owner | Deadline | Status
Finalize accounting statements for Q3 2023 | Sarah Johnson (Finance) | 2023-10-14 | In Progress
Review and update internal control policies | Michael Chen (Compliance) | 2023-10-18 | Completed
Certify vendor contracts for audit validation | Linda Torres (Procurement) | 2023-10-16 | Pending Review
Conduct final team readiness briefing | James Reed (Audit Lead) | 2023-10-25 | Scheduled
Audit Timeline Overview
Phase | Start Date | End Date | Status
Preparation & Documentation | 2023-09-01 | 2023-10-15 | In Progress
Internal Review & Gap Analysis | 2023-10-16 | 2023-10-24 | Not Started
External Audit Engagement | 2023-10-25 | 2023-11-15 | Not Started
Audit Closeout & Reporting | 2023-11-16 | 2023-11-30 | Not Started
Notes & Recommendations
Urgent:Internal Controls Verification is overdue and must be addressed immediately to avoid audit delays.
Recommended:Schedule a cross-functional meeting next week to align on outstanding action items and ensure document completeness.
Note:All teams are required to submit final deliverables by October 20th for comprehensive review prior to external audit commencement.