## Worksheet
Audit Preparation - Planning View
Template Type: Business Template ¦ Purpose: Audit Preparation ¦ Style/Version: Planning View
Phase | Activity / Task | Responsible Party | Due Date | Status | Notes / Comments
Planning & Scoping | Define audit objectives and scope | Audit Manager | 2024-04-15 | In Progress | Review with stakeholders
Planning & Scoping | Identify key processes and controls to audit | Audit Team Lead | 2024-04-18 | To Do | Review prior audit reports
Data Collection & Review | Gather documentation and evidence for review | Internal Audit Staff | 2024-04-25 | In Progress | Include financial records and compliance logs
Data Collection & Review | Conduct preliminary risk assessment | Risk Analyst | 2024-04-20 | To Do | Review internal risk matrix
Testing & Evaluation | Perform control testing and sampling procedures | Audit Team Lead, Staff | 2024-05-10 | To Do | Use sample size calculator for accuracy
Reporting & Follow-Up | Compile audit findings and recommendations | Audit Writer | 2024-05-18 | To Do | Draft report for review by management
Reporting & Follow-Up | Present findings to audit committee and senior management | Audit Manager, Senior Leadership | 2024-05-25 | To Do | Schedule meeting in advance