## Audit Preparation - Chore Chart
Audit Preparation - Chore Chart (Business Use)
Chore / Task | Owner | Due Date | Status | Notes / Attachments
Preliminary Document Collection | Finance Team | 2024-04-05 | In Progress | Include all Q1 financial statements and tax filings.
Review Internal Controls Documentation | Internal Audit Lead | 2024-04-08 | Pending | Update latest control matrix.
Validate Account Reconciliations | Accounting Specialist | 2024-04-10 | Pending | Verify all reconciliations up to March 31.
Prepare Management Representation Letter | CEO & CFO | 2024-04-12 | Pending | Draft and sign by both executives.
Confirm Bank Balances & Outstanding Checks | Finance Manager | 2024-04-13 | Pending | Email confirmation required from each bank.
Review Payroll & Benefits Records | HR Department | 2024-04-15 | Pending | Including year-to-date summaries.
Finalize Audit Checklist Completion | Internal Audit Team | 2024-04-18 | Pending | Cross-check all items with audit team.
Conduct Pre-Audit Walkthrough Meeting | Internal Audit Lead | 2024-04-19 | Pending | Invite all department heads.
Audit Readiness Sign-off | COO & CFO | 2024-04-21 | Pending | Final approval before auditor arrival.
Archive All Supporting Documents | Document Manager | 2024-04-25 | Pending | Maintain version control and access logs.