## Worksheet
Audit Preparation - Large Business Chore Chart
Chore/Task | Responsible Team | Due Date | Status | Notes/Comments
Review Financial Statements (Q1) | Finance Department | 2024-04-15 | Pending | Verify all revenue entries against contracts.
Update Internal Controls Documentation | Compliance & Legal | 2024-04-18 | Pending | Incorporate changes from Q1 review.
Conduct Inventory Count (Physical) | Operations Team | 2024-04-16 | Completed | All items reconciled with system records.
Review Payroll Processing Accuracy | HR & Payroll | 2024-04-17 | Pending | Check overtime and benefits allocation.
Verify Vendor Invoices & Contracts | Procurement & Finance | 2024-04-19 | Pending | Ensure all contracts are current and compliant.
IT System Access Audit | IT Security | 2024-04-20 | Pending | Review user permissions and log activity.
Complete Audit Checklist (Internal Review) | Audit Committee | 2024-04-21 | Pending | Finalize all internal documentation.
Prepare Management Report for Audit Board | Executive Team | 2024-04-23 | Pending | Included risk assessments and action plans.
Conduct Mock Audit Walkthrough | Audit & Compliance Teams | 2024-04-25 | Pending | Simulate real audit process for team readiness.
Final Audit Package Submission | Audit Coordinator | 2024-04-30 | Pending | All documents compiled and verified.