## Worksheet
Audit Preparation - Chore Chart (Manager View)
Chore Task | Responsible Team Member | Due Date | Status | Completion Date | Notes/Comments
Review financial statements for Q1 | Jane Smith | 2024-04-05 | Complete | 2024-04-03 | Verified with CFO approval.
Update compliance documentation | Mike Johnson | 2024-04-10 | Pending | - | In progress, final review scheduled.
Conduct internal audit of HR records | Lisa Chen | 2024-04-15 | Pending | - | Field review scheduled this week.
Validate inventory counts from warehouse | Carlos Rivera | 2024-04-12 | Overdue | - | Needs immediate follow-up.
Verify vendor contract renewals | Sarah Williams | 2024-04-18 | Pending | - | Awaiting legal team input.