## Audit Preparation - Chore Chart
Audit Preparation - Chore Chart
Date | Task Description | Responsible Person | Status | Notes / Comments
2024-04-01 | Review financial statements for Q1 2024 | John Smith | Pending | N/A
2024-04-03 | Gather supporting documentation for expenses | Jane Doe | In Progress | Collection in progress from department heads.
2024-04-05 | Verify bank reconciliations accuracy | Mike Johnson | Pending | To be confirmed with CFO.
2024-04-07 | Conduct internal walkthrough of accounting processes | Sarah Wilson | Pending | Needs scheduling with audit team.
2024-04-10 | Update audit checklist and documentation tracker | Alex Brown | Pending | Revisions due by end of week.
2024-04-12 | Prepare preliminary audit report draft | Lisa Garcia | Pending | Based on findings from prior steps.
2024-04-15 | Review and validate all audit evidence collected | James Lee | Pending | Final verification before submission.
2024-04-17 | Clean up and archive audit files | Tina Patel | Pending | Ensure version control and backup.
This template is designed for one-page audit preparation using a chore chart format. All tasks should be updated regularly to ensure accuracy.