## Worksheet
Audit Preparation - Daily Planner (Analysis View)
Date | Activity Type | Task Description | Responsible Party | Status | Completion % | Notes / Remarks
2023-10-05 (Thu) | Planning | Review audit objectives and scope | Audit Lead | In Progress | 75% | Certain scope items require clarification from management.
| Documentation Review | Collect and organize prior year audit reports | Audit Team | On Hold | 0% | Waiting for access to archived files.
| Data Gathering | Begin compiling financial data from departments | Data Analysts | Not Started | 0% | Draft templates prepared; awaiting departmental input.
2023-10-06 (Fri) | Risk Assessment | Identify key risk areas and prioritize for review | Risk Manager | Not Started | 0% | Requires input from compliance team.
| Scheduling | Craft interview schedule with key personnel | Scheduler (Audit Coordinator) | Not Started | 0% | Availability to be confirmed by department heads.
Mid-Week Review and Adjustment
2023-10-09 (Mon) | Progress Analysis | Review completion status, adjust timelines as needed | Audit Lead | In Progress | 60% | Made adjustments to task sequence for efficiency.
| Team Alignment | Hold sync-up meeting with audit team members | All Team Members | Completed | 100% | Cleared communication gaps; updated action items.
Detailed Analysis Phase
2023-10-10 (Tue) | Financial Review | Analyze revenue and expense trends for Q3 | Financial Analyst | In Progress | 85% | Audited 7/8 key accounts.
| Control Testing | Test internal controls over payroll processing | Internal Control Specialist | In Progress | 50% | Focused on biweekly batch processing.
| Data Validation | Verify source system data integrity | Data Integrity Team | Not Started | 0% | Pending validation protocol approval.
Finalization & Reporting
2023-10-12 (Thu) | Findings Compilation | Document preliminary findings and evidence | Audit Lead | Not Started | 0% | To begin after control testing completes.
| Draft Report Creation | Create first draft of audit report outline | Report Writer | Not Started | 0% | Preliminary structure finalized.
Overall Progress Summary: 62% Complete
This is a sample template for Audit Preparation using a Daily Planner - Analysis View. Update regularly to reflect real-time audit progress.