## Worksheet
Audit Preparation - Advanced Gantt Chart
Task | Start Date | End Date | Duration (Days) | Status
Define Audit Scope & Objectives | 2024-04-01 | 2024-04-05 | 5
Assemble Audit Team | 2024-04-03 | 2024-04-15 | 13
Review Historical Audit Records | 2024-04-10 | 2024-04-18 | 9
Conduct Risk Assessment | 2024-04-16 | 2024-04-25 | 10
Develop Audit Plan & Schedule | 2024-04-18 | 2024-05-03 | 16
Send Audit Notification to Management | 2024-04-19 | 2024-05-15 | 37
Prepare Audit Checklists & Tools | 2024-04-20 | 2024-05-16 | 37
Conduct Onsite Audit (Phase 1) | 2024-05-16 | 2024-06-30 | 45
Draft Audit Findings & Recommendations | 2024-06-15 | 2024-07-15 | 31
Submit Draft Report to Stakeholders | 2024-07-16 | 2024-07-31 | 16
Finalize Audit Report | 2024-08-01 | 2024-08-15 | 15
Audit Completion Deadline