## Audit Preparation Gantt Chart
Task | Start Date | End Date | Status
Define Audit Scope | 2023-10-01 | 2023-10-05 | In Progress
Review Internal Controls | 2023-10-06 | 2023-10-15 | Not Started
Data Collection Phase 1 | 2023-10-16 | 2023-10-25 | Not Started
Data Collection Phase 2 | 2023-10-26 | 2023-11-05 | Not Started
Audit Testing and Analysis | 2023-11-06 | 2023-11-15 | Not Started
Management Review Meeting | 2023-11-16 | 2023-11-20 | Not Started
Finalize Audit Report | 2023-11-21 | 2023-11-25 | Not Started
Audit Closure and Sign-off | 2023-11-26 | 2023-11-30 | Not Started