## Audit Preparation Gantt Chart
Audit Preparation Gantt Chart
Task | Start Date | End Date | Status | Progress
Initiate Audit Planning | 2024-03-01 | 2024-03-15 | Completed
Define Scope & Objectives | 2024-03-16 | 2024-03-31 | In Progress
Identify Key Processes | 2024-04-01 | 2024-04-15 | Not Started
Gather Documentation | 2024-04-16 | 2024-05-15 | Not Started
Conduct Risk Assessment | 2024-05-16 | 2024-06-15 | Not Started
Perform Field Audit | 2024-06-16 | 2024-07-31 | Not Started
Draft Audit Report | 2024-08-01 | 2024-08-15 | Not Started
Review & Approve Findings | 2024-08-16 | 2024-08-31 | Not Started
Finalize Audit Report | 2024-09-01 | 2024-09-15 | Not Started
Submit Audit Report to Management | 2024-09-16 | 2024-09-30 | Not Started