## Worksheet
Audit Preparation - Gantt Chart (Client View)
Task | Start Date | End Date | Duration (Days) | Status | Progress
Document Collection | 2024-03-01 | 2024-03-15 | 15 | In Progress
Financial Review | 2024-03-16 | 2024-03-31 | 16 | In Progress
Internal Controls Assessment | 2024-04-01 | 2024-04-15 | 15 | In Progress
Compliance Verification | 2024-04-16 | 2024-05-15 | 30 | Delayed
Audit Report Drafting | 2024-05-16 | 2024-06-30 | 46 | Completed
Client Review & Feedback | 2024-07-01 | 2024-07-15 | 15 | Completed
Final Audit Report Submission | 2024-07-16 | 2024-07-31 | 16 | Completed
Post-Audit Follow-Up | 2024-08-01 | 2024-09-30 | 61 | Completed
Knowledge Transfer Session | 2024-10-01 | 2024-10-31 | 30 | Completed
Audit Closure & Sign-Off | 2024-11-01 | 2024-11-30 | 30 | Completed