## Audit Preparation Gantt Chart
Audit Preparation Gantt Chart (Detailed)
Task ID | Task Description | Start Date | End Date | Duration (Days) | Status | Responsible Party
T001 | Define Audit Scope & Objectives | 2024-04-01 | 2024-04-05 | 5 | In Progress | Audit Manager
T002 | Assemble Audit Team & Assign Roles | 2024-04-03 | 2024-04-15 | 13 | In Progress | Hiring Coordinator
T003 | Review Prior Audit Findings & Reports | 2024-04-16 | 2024-04-18 | 3 | Pending | Audit Lead
T004 | Collect & Review Documentation (Financial Records) | 2024-04-19 | 2024-05-17 | 30 | Pending | Finance Team
T005 | Conduct Initial Risk Assessment | 2024-05-18 | 2024-06-15 | 30 | Pending | Risk Analysts
T006 | Perform Fieldwork & Testing Procedures | 2024-06-16 | 2024-07-31 | 46 | Pending | Audit Team (All)
T007 | Issue Preliminary Findings & Feedback Session | 2024-08-01 | 2024-08-15 | 15 | Pending | Audit Lead & Stakeholders
T008 | Finalize Audit Report & Recommendations | 2024-08-16 | 2024-09-30 | 45 | Pending | Audit Manager & Reporting Team
T009 | Submit Final Report to Executive Board | 2024-10-01 | 2024-10-05 | 5 | Pending | Audit Manager
T010 | Post-Audit Follow-Up & Action Tracking | 2024-10-06 | 2025-03-31 | 178 | Pending | Audit Team & Department Heads
Progress Summary: