## Worksheet
Audit Preparation - Gantt Chart Template (Extended)
Task ID | Task Description | Owner | Start Date | End Date | Status | % Complete
001 | Define Audit Scope and Objectives | Jane Smith | 2024-04-01 | 2024-04-15 | in-progress
002 | Review Prior Audit Findings | David Lee | 2024-04-16 | 2024-04-30 | pending
003 | Collect Financial Documents | Sarah Johnson | 2024-05-01 | 2024-05-15 | pending
004 | Conduct Preliminary Risk Assessment | Robert Brown | 2024-05-16 | 2024-05-31 | pending
005 | Develop Audit Plan & Schedule | Jane Smith | 2024-06-01 | 2024-06-15 | pending
006 | Perform Fieldwork and Testing | All Team Members | 2024-06-16 | 2024-07-31 | pending
007 | Document Audit Findings | Sarah Johnson | 2024-08-01 | 2024-08-15 | pending
008 | Prepare Final Audit Report | David Lee | 2024-08-16 | 2024-08-31 | pending
009 | Review and Approve Report | Jane Smith | 2024-09-01 | 2024-09-15 | pending
010 | Audit Closeout and Feedback Session | All Stakeholders | 2024-09-16 | 2024-09-30 | pending
Total Duration: |  |  |  |  | 6 months (April 1, 2024 - September 30, 2024)