## Worksheet
Audit Preparation - Gantt Chart (Freelancer Style)
Task | Start Date | End Date | Duration (Days) | Status | Progress
Initial Planning & Scope Definition | 2024-04-01 | 2024-04-05 | 5 | Completed
Document Collection & Organization | 2024-04-06 | 2024-04-15 | 10 | In Progress
Financial Statement Review | 2024-04-16 | 2024-04-25 | 10 | Pending
Internal Control Assessment | 2024-04-26 | 2024-05-10 | 15 | Pending
Risk Analysis & Evaluation | 2024-05-11 | 2024-05-20 | 10 | Pending
Draft Audit Report Preparation | 2024-05-21 | 2024-05-31 | 11 | Pending
Final Review & Approval | 2024-06-01 | 2024-06-05 | 5 | Pending
Client Presentation & Sign-Off | 2024-06-06 | 2024-06-10 | 5 | Pending
Total Duration: |  |  | 56 days
Legend
● Completed¦● In Progress¦● Pending