## Worksheet
Audit Preparation Gantt Chart - Home Use
Task ID | Task Description | Start Date | End Date | Status | % Complete
Phase 1: Planning & Preparation (Jan 01 - Jan 15)
TP-001 | Define Audit Scope and Objectives | 2024-01-01 | 2024-01-05 | In Progress | 85%
TP-002 | Identify Key Stakeholders and Team Members | 2024-01-03 | 2024-01-15 | In Progress | 65%
Phase 2: Documentation Review (Jan 16 - Jan 31)
TP-003 | Collect and Organize Financial Records | 2024-01-16 | 2024-01-25 | In Progress | 75%
MK-001 | Milestone: Documentation Complete | 2024-01-31 | 2024-01-31 | Not Started | 0%
Phase 3: Fieldwork & Testing (Feb 01 - Feb 28)
TP-004 | Conduct Internal Control Assessment | 2024-02-01 | 2024-02-15 | Not Started | 0%
TP-005 | Perform Substantive Testing on Transactions | 2024-02-16 | 2024-02-28 | Not Started | 0%
Phase 4: Report Preparation (Mar 01 - Mar 15)
TP-006 | Compile Audit Findings and Recommendations | 2024-03-01 | 2024-03-10 | Not Started | 0%
MK-002 | Milestone: Draft Report Submitted | 2024-03-15 | 2024-03-15 | Not Started | 0%
Phase 5: Final Audit Approval (Mar 16 - Mar 31)
TP-007 | Review and Approve Final Audit Report | 2024-03-16 | 2024-03-31 | Not Started | 0%
Total Duration: |  | Jan 01 - Mar 31, 2024 (90 days)