## Audit Preparation Gantt Chart
Task ID | Task Description | Start Date | End Date | Status | Responsible Party | Progress Timeline
1 | Define Audit Scope & Objectives | 2023-10-05 | 2023-10-15 | In Progress | Audit Manager
1.1 | Identify Key Processes to Audit | 2023-10-06 | 2023-10-18 | In Progress | Process Lead, Finance
1.2 | Review Previous Audit Reports | 2023-10-07 | 2023-10-14 | Closed | Audit Specialist, Compliance
2 | Fieldwork & Data Collection | 2023-10-16 | 2023-11-30 | Pending | Audit Team - Field Staff
2.1 | Interview Key Personnel | 2023-10-16 | 2023-10-31 | Pending | Audit Lead, Internal Audit
2.2 | Collect Financial Documents & Records | 2023-10-17 | 2023-11-15 | Pending | Finance Team, Data Clerk
2.3 | Perform Test of Controls | 2023-11-01 | 2023-11-30 | Pending | Audit Analyst, IT Compliance
3 | Report Drafting & Review | 2023-12-01 | 2023-12-15 | Pending | Audit Manager, Report Lead
3.1 | Write Findings & Recommendations | 2023-12-01 | 2023-12-08 | Pending | Audit Specialist, Reporting
3.2 | Internal Review & Feedback Loop | 2023-12-09 | 2023-12-15 | Pending | Audit Committee, Legal Counsel
4 | Final Audit Report Submission | 2023-12-16 | 2023-12-18 | Pending | Audit Manager, Director of Audit
Final Audit Report Approval & Sign-Off(Due: 2023-12-18)