## Worksheet
Audit Preparation Gantt Chart - One Page
Task | Start Date | End Date | Status | Progress (%)
Review Audit Plan & Objectives | 2023-10-02 | 2023-10-06 | In Progress | 45%
Collect Financial Records (Q3) | 2023-10-07 | 2023-10-14 | In Progress | 65%
Interview Key Personnel | 2023-10-15 | 2023-10-19 | Not Started | 0%
Internal Controls Assessment | 2023-10-20 | 2023-10-27 | Not Started | 0%
Test Transaction Samples | 2023-10-28 | 2023-11-03 | Not Started | 0%
Draft Audit Findings Report | 2023-11-04 | 2023-11-09 | Not Started | 0%
Final Review & Approval | 2023-11-10 | 2023-11-14 | Not Started | 0%
This Gantt Chart is intended for Audit Preparation purposes. Last updated on October 2, 2023.