## Worksheet
Audit Preparation - Gantt Chart (Planning View)
Task | Start Date | End Date | Duration (Days) | Status | Progress
Define Audit Scope & Objectives | 2024-04-01 | 2024-04-05 | 5 | In Progress
Identify Key Stakeholders | 2024-04-03 | 2024-04-15 | 13 | In Progress
Gather Historical Audit Data | 2024-04-10 | 2024-04-30 | 21 | Pending
Develop Audit Plan & Schedule | 2024-04-15 | 2024-04-30 | 16 | Pending
Audit Plan Approval - Milestone | 2024-05-01 | 2024-05-01 | 1 | Milestone
Assign Audit Team & Roles | 2024-05-02 | 2024-05-10 | 9 | Pending
Develop Audit Checklists & Tools | 2024-05-10 | 2024-05-31 | 22 | Pending
Conduct Pre-Audit Training | 2024-05-15 | 2024-05-17 | 3 | Pending
Finalize Documentation & Templates | 2024-05-25 | 2024-06-15 | 21 | Pending
Preparation Phase Complete - Milestone | 2024-06-15 | 2024-06-15 | 1 | Milestone
Total Duration |  |  | 75 days