## Worksheet
Audit Preparation - Gantt Chart Report Version
Task ID | Task Description | Start Date | End Date | Status | Progress (%)
AUD-001 | Define Audit Scope & Objectives | 2023-10-02 | 2023-10-15 | In Progress
AUD-002 | Identify Key Processes & Controls | 2023-10-16 | 2023-10-31 | In Progress
AUD-003 | Collect Supporting Documentation | 2023-11-01 | 2023-11-15 | Delayed
AUD-004 | Initial Risk Assessment | 2023-11-16 | 2023-11-30 | Completed
AUD-005 | Develop Audit Plan & Schedule | 2023-12-01 | 2023-12-15 | In Progress
AUD-006 | Coordinate with Department Leads | 2023-12-16 | 2023-12-31 | Completed
AUD-007 | Finalize Audit Checklist | 2024-01-01 | 2024-01-15 | Completed
AUD-008 | Conduct Pre-Audit Review | 2024-01-16 | 2024-01-31 | Completed
Overall Progress: |  |  |  | 73%
Report Version ¦ Generated on October 5, 2023 ¦ Audit Preparation Gantt Chart