## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Plan Audit Scope | 2024-04-01 | 2024-04-05 | 5 | Audit Manager | Completed
Collect Financial Documents | 2024-04-06 | 2024-04-15 | 10 | Accountant | In Progress
Review Internal Controls | 2024-04-16 | 2024-04-25 | 10 | Compliance Officer | Not Started
Conduct Field Audit | 2024-04-26 | 2024-05-10 | 15 | Audit Team Lead | Not Started
Prepare Audit Report | 2024-05-11 | 2024-05-17 | 7 | Audit Manager | Not Started
Review and Approve Report | 2024-05-18 | 2024-05-20 | 3 | Senior Auditor | Not Started
Finalize Audit Documentation | 2024-05-21 | 2024-05-23 | 3 | Audit Manager | Not Started
Submit Audit to Management | 2024-05-24 | 2024-05-24 | 1 | Audit Team Lead | Not Started