## Worksheet
Audit Preparation - Gantt Chart (Startup Style)
Task | Start Date | End Date | Duration (Days) | Status | Progress
Data Collection Phase | 2024-04-01 | 2024-04-15 | 15 | In Progress
Document Review & Organization | 2024-04-16 | 2024-04-30 | 15 | In Progress
Internal Control Assessment | 2024-05-01 | 2024-05-10 | 10 | In Progress
Gap Analysis & Remediation | 2024-05-11 | 2024-05-25 | 15 | Delayed
Final Audit Package Preparation | 2024-05-26 | 2024-06-10 | 15 | Not Started
Audit Kickoff Meeting | 2024-06-11 | 2024-06-11 | 1 | Delayed
Audit Execution & Documentation | 2024-06-12 | 2024-06-30 | 19 | Not Started
Final Reporting & Sign-Off | 2024-07-01 | 2024-07-15 | 15 | Not Started
Total Timeline | 2024-04-01 | 2024-07-15 | 137 | Audit Preparation in Progress