## Worksheet
Audit Preparation - Gantt Chart (Team Use)
Task ID | Task Description | Owner | Start Date | End Date | Status | Progress (%)
001 | Document Collection & Review | Jane Smith | 2025-04-01 | 2025-04-15 | In Progress
002 | Internal Control Testing | Mike Johnson | 2025-04-10 | 2025-04-30 | In Progress
003 | Risk Assessment Workshop | Sarah Lee | 2025-04-18 | 2025-04-19 | Completed
004 | Financial Statement Analysis | David Brown | 2025-04-15 | 2025-04-28 | In Progress
005 | Final Audit Report Drafting | Emma Wilson | 2025-04-29 | 2025-05-10 | Delayed
006 | Management Review Meeting | Linda Chen | 2025-05-11 | 2025-05-13 | Not Started
007 | Audit Closure & Sign-off | James Taylor | 2025-05-14 | 2025-05-16 | Not Started