## Worksheet
Audit Preparation - Gantt Chart Template
Task ID | Task Description | Start Date | End Date | Status | % Complete
1 | Define Audit Scope and Objectives | 2023-09-01 | 2023-09-15 | Pending | 15%
1.1 | Identify Key Processes & Controls | 2023-09-16 | 2023-09-30 | In Progress | 45%
1.2 | Risk Assessment & Prioritization | 2023-10-01 | 2023-10-15 | In Progress | 65%
2 | Data Collection and Documentation Review | 2023-10-16 | 2023-11-15 | Pending | 5%
3 | Internal Testing and Validation | 2023-11-16 | 2023-12-07 | Pending | 0%
4 | Audit Report Drafting & Review | 2023-12-08 | 2023-12-31 | Pending | 0%
5 | Audit Completion & Final Sign-off | 2024-01-15 | 2024-01-31 | Milestone | 95%
Template Version: 1.2 ¦ Purpose: Audit Preparation ¦ Gantt Chart Style