## Worksheet
Audit Preparation - Gantt Chart (Tracking View)
Task | Owner | Start Date | End Date | Duration (Days) | Progress (%) | Status
Phase 1: Planning
Define Audit Scope | John Smith | 2024-01-05 | 2024-01-10 | 6 |  | In Progress
Identify Key Risk Areas | Jane Doe | 2024-01-07 | 2024-01-15 | 9 |  | In Progress
Phase 2: Data Collection
Collect Financial Records | Mike Johnson | 2024-01-16 | 2024-01-31 | 16 |  | In Progress
Gather Operational Documents | Emily Brown | 2024-01-18 | 2024-02-05 | 19 |  | In Progress
Phase 3: Review & Analysis
Perform Internal Review | Robert Lee | 2024-02-06 | 2024-02-15 | 10 |  | In Progress
Conduct Risk Assessment | Sarah Wilson | 2024-02-16 | 2024-03-01 | 14 |  | Not Started
Phase 4: Reporting
Prepare Draft Audit Report | David Taylor | 2024-03-02 | 2024-03-15 | 14 |  | Not Started
Submit Final Audit Report | Lisa Anderson | 2024-03-16 | 2024-03-25 | 10 |  | Not Started
Milestones
Audit Kickoff | Team Lead | 2024-01-05 | 2024-01-05 | N/A |  | Completed
Scope Approval | John Smith | 2024-01-12 | 2024-01-12 | N/A |  | Completed
Data Collection Complete | Emily Brown | 2024-02-05 | 2024-02-05 | N/A |  | Completed
Note:This Gantt chart is a tracking view for audit preparation, updated as of 2024-01-25.