## Worksheet
AUDIT PREPARATION - MONTHLY PLANNER (ANALYSIS VIEW)
Week | Month | Objective / Task | Responsible Party | Status | Start Date | Due Date | % Complete | Risk Level | Audit Area | Documentation Required? | Notes / Comments
Week 1: Planning & Scope Definition
Week 1 | January | Define audit scope and objectives for the month | Audit Manager | To Do | 2024-01-01 | 2024-01-05 | 0% | Low | All Departments | Yes
Week 2: Documentation Review & Risk Assessment
Week 2 | January | Review existing policies and procedures for compliance gaps | Compliance Officer | In Progress | 2024-01-08 | 2024-01-12 | 65% | Moderate | Policies & Governance | Yes | Identified 3 minor inconsistencies in HR policy.
Week 3: Fieldwork & Data Collection
Week 3 | January | Collect financial records from Finance Department | Audit Team Lead, Finance | In Progress | 2024-01-15 | 2024-01-19 | 85% | High | Financial Controls | Yes | Data received for Q4; pending validation.
Week 4: Analysis & Reporting Preparation
Week 4 | January | Perform data validation and risk analysis on collected evidence | Data Analyst, Audit Team | To Do | 2024-01-22 | 2024-01-31 | 0% | Moderate | Financial & Operational Controls | Yes
Monthly Summary: |  | Total Tasks: 4 ¦ Completed: 1 ¦ In Progress: 2 ¦ On Hold: 1
This template is designed for audit preparation and monthly planning. Update status regularly to ensure accuracy.