## Worksheet
Audit Preparation - Monthly Planner (Client View)
Week | Task Description | Responsible Person | Status | Due Date | Supporting Documents
Week 1 | Review prior audit findings and close outstanding items | Jane Smith | In Progress | 2024-04-05 | Report_Revision_1.docx, FollowUp_Ticket_789.pdf
| Collect financial statements for Q1 2024 | Mike Johnson | Not Started | 2024-04-07 | Q1_Financials.xlsx, Trial_Balance.pdf
| Schedule internal review meeting with department heads | Lisa Brown | Completed | 2024-04-03 | Meeting_Agenda.docx, Attendance_List.csv
Week 2 | Gather HR and payroll records for audit trail verification | David Lee | In Progress | 2024-04-12 | Payroll_Summary.csv, Employee_Termination_Log.xlsx
| Update internal controls documentation | Sarah Wilson | Not Started | 2024-04-15 | Controls_Doc_v3.docx, Risk_Matrix.xlsx
| Verify fixed asset register accuracy | Ryan Carter | In Progress | 2024-04-14 | Fixed_Asset_Register.xlsx, Asset_Pictures.zip
Week 3 | Review revenue recognition policies and supporting evidence | Emily Davis | In Progress | 2024-04-19 | Revenue_Policy.pdf, Contract_Signings.xlsx
| Conduct preliminary risk assessment for audit scope | Amanda Torres | Not Started | 2024-04-21 | Risk_Assessment_Template.xlsx, Dept_Surveys.pdf
| Prepare list of key audit contacts and escalation points | Maria Garcia | Completed | 2024-04-18 | Audit_Contact_List.xlsx, Internal_Network_Docs.pdf
Week 4 | Finalize audit readiness checklist and sign-off | James White | Not Started | 2024-04-26 | Audit_Readiness_Checklist_v2.xlsx, SignOff_Form.pdf
| Conduct mock audit walkthrough with internal team | Laura Moore | Not Started | 2024-04-25 | Walkthrough_Script.docx, Feedback_Report.pdf
| Submit final documentation package to auditors | Kevin Patel | Not Started | 2024-04-30 | All_Docs_Combined.zip, Final_Submission.pdf
Note: This monthly planner is for internal audit preparation and client review. All tasks must be completed by the due dates to ensure timely audit completion.