## Worksheet
AUDIT PREPARATION - MONTHLY DAILY PLANNER (Daily View)
Date | Day | Objective / Task | Status | Owner | Start Time | End Time | Duration (hrs) | Audit Area | Evidence Required? | Comments/Notes
01/04/2025 | Mon | Review financial records Q1 | Pending | Jane Doe | 09:00 AM | 11:30 AM | 2.5 | Financials | No | Cleaned data, verified totals.
02/04/2025 | Tue | Confirm vendor contracts compliance | In Progress | Mike Smith | 10:00 AM | 12:30 PM | 2.5 | Vendors & Procurement | Yes | In progress; awaiting legal review.
03/04/2025 | Wed | Test access controls on HR systems | Pending | Lisa Chen | 08:30 AM | 10:15 AM | 1.75 | IT Security | Yes | Scheduled with IT team.
04/04/2025 | Thu | Verify payroll processing accuracy | Completed | David Kim | 09:30 AM | 11:45 AM | 2.25 | Payroll & HR | Yes | All records match last month’s audit.
05/04/2025 | Fri | Compile preliminary findings report | Pending | Jane Doe | 13:00 PM | 15:30 PM | 2.5 | Miscellaneous | No | Draft in progress.