## Worksheet
Audit Preparation - Monthly Planner (Detailed)
Week | Date Range | Task Description | Responsible Party | Status | Deadline | Notes/Comments
Week 1 | 01-07 Apr 2025 | Collections & Review of Prior Audit Findings | Audit Team Lead | Pending | 04 Apr 2025 | Verify corrective action evidence.
|  | Compile departmental financial statements | Finance Manager | In Progress | 05 Apr 2025 | Include all branch summaries.
|  | Gather documentation for inventory controls | Operations Coordinator | Pending | 06 Apr 2025 | Include count sheets and reconciliation logs.
|  | Review compliance with internal policies | Compliance Officer | Pending | 07 Apr 2025 | Draft findings report.
Week 2 | 08-14 Apr 2025 | Field Audit Testing & Process Observation | Audit Team (All) | In Progress | 11 Apr 2025 | Perform walkthroughs across key departments.
|  | Test procurement approval workflows | Procurement Auditor | Pending | 12 Apr 2025 | Capture deviations and exceptions.
|  | Verify payroll processing accuracy | Payroll Specialist | Pending | 13 Apr 2025 | Sample size: 50 employees.
|  | Cross-verify sales ledger entries | Accounting Analyst | Pending | 14 Apr 2025 | Compare with shipping records.
Week 3 | 15-21 Apr 2025 | Draft Findings and Prepare Audit Report | Audit Lead & Reporting Team | Pending | 20 Apr 2025 | Include risk ratings and recommendations.
|  | Develop summary of material weaknesses | Risk Assessment Officer | Pending | 18 Apr 2025 | Support with evidence references.
|  | Create executive summary presentation | Report Designer | Pending | 20 Apr 2025 | 10-slide deck for leadership review.
Week 4 | 22-30 Apr 2025 | Final Review, Management Response & Closeout | Audit Committee & Executives | Pending | 30 Apr 2025 | Finalize all action items.
|  | Obtain management responses to findings | Internal Communications | Pending | 25 Apr 2025 | Require signed acknowledgment.
|  | Submit final audit report to Audit Committee | Audit Lead | Pending | 28 Apr 2025 | Include appendices and supporting data.
|  | Archive all audit materials in secure drive | Records Manager | Pending | 30 Apr 2025 | Apply retention policy.
Audit Preparation Monthly Planner – Detailed Template ¦ Version 1.0 ¦ Prepared for April 2025
Print this table for physical tracking or export to Excel via browser print function.