## Worksheet
Monthly Audit Preparation Planner
Date | Audit Area | Objective | Responsible Party | Status | Deadline | Priority | Documentation Needed | Review Date | Completed? | Remarks | Action Items
01/04 | Financial Records | Verify monthly financial statements and supporting documents | Finance Team Lead | In Progress | 05/04 | High | Yes | - | No |  | Schedule review meeting
05/04 | IT Systems Access | Validate user access logs and permission levels | IT Security Officer | Completed | 05/04 | Medium | Yes | 06/04 | Yes | Access logs reviewed and cleaned.
08/04 | Payroll Processing | Audit payroll calculations and tax filings for accuracy | HR Manager | In Progress | 12/04 | High | Yes | - | No |  | Update payroll templates
10/04 | Inventory Control | Conduct physical inventory count and reconcile with system records | Warehouse Supervisor | Pending | 14/04 | High | Yes | 15/04 | No |  | Prepare count sheets
15/04 | Compliance Documentation | Verify compliance with regulatory standards (e.g., SOX, GDPR) | Legal & Compliance Officer | Pending | 18/04 | High | Yes | - | No |  | Gather recent compliance reports
Summary of Monthly Audit Status as of 15/04
Total Tasks |  |  | 5
Completed |  |  | 1 (20%)
In Progress |  |  | 2 (40%)
Pending |  |  | 2 (40%)