## Worksheet
Audit Preparation - Monthly Planner
Month:January 2024
Week | Task Description | Status | Assigned To | Due Date | Notes/Comments
Week 1 | Preliminary risk assessment and document collection | Not Started | Team A | Jan 7, 2024
Tasks Related to Internal Controls
| Review access controls for sensitive data systems | In Progress | John Smith | Jan 8, 2024
Tasks Related to Compliance
Update compliance checklists based on new regulations | Not Started | Lisa Chen | Jan 9, 2024
Tasks Related to Financial Records
Verify accuracy of month-end closing entries | Not Started | Alex Rivera | Jan 10, 2024
Page 1 of 4Audit Preparation Monthly Planner – Version: Multi-Page ¦ Generated: Jan 1, 2024
Audit Preparation - Monthly Planner
Month:January 2024
Week | Task Description | Status | Assigned To | Due Date | Notes/Comments
Week 2 | Conduct internal walkthroughs of key processes | Not Started | Team B | Jan 14, 2024
Tasks Related to IT Systems
| Review system logs and security alerts from last month | In Progress | Maria Gomez | Jan 15, 2024
Tasks Related to Vendor Management
Verify vendor contracts and renewal dates | Not Started | Daniel Lee | Jan 16, 2024
Additional Notes:
Ensure all documents are stored in the central audit repository.
Team leads must update task statuses by end of each day.
Scheduled review meeting: Jan 17, 2024 – 10:00 AM
Page 2 of 4Audit Preparation Monthly Planner – Version: Multi-Page ¦ Generated: Jan 1, 2024
Audit Preparation - Monthly Planner
Month:January 2024
Week | Task Description | Status | Assigned To | Due Date | Notes/Comments
Week 3 | Finalize audit procedures for all departments | Not Started | Team C | Jan 21, 2024
Tasks Related to Documentation
| Compile all evidence and supporting materials | Not Started | Sarah Thompson | Jan 22, 2024
Tasks Related to Interview Scheduling
Schedule interviews with department heads | Not Started | James Wilson | Jan 23, 2024
Monthly Progress Summary:
As of Jan 20, 2024:
Total Tasks Assigned: 15
Tasks Completed: 7 (46.7%)
Tasks In Progress: 5 (33.3%)
Tasks Pending: 3 (20.0%)
Page 3 of 4Audit Preparation Monthly Planner – Version: Multi-Page ¦ Generated: Jan 1, 2024
Audit Preparation - Monthly Planner
Month:January 2024
Week | Task Description | Status | Assigned To | Due Date | Notes/Comments
Week 4 | Conduct final audit fieldwork and testing | Not Started | Team D | Jan 28, 2024
Tasks Related to Reporting
| Prepare draft audit report for internal review | Not Started | Nina Patel | Jan 30, 2024
Tasks Related to Closing
Conduct audit closure meeting with management | Not Started | All Team Leads | Jan 31, 2024
Final Actions Before Audit Completion:
Confirm all findings are properly documented with evidence.
Review draft report for accuracy and clarity.
Ensure all team members have submitted final task reports.
Audit Lead:_________________________
Date:_________________________