## Worksheet
AUDIT PREPARATION - MONTHLY PLANNER (OFFICE USE)
Week | Task Description | Responsible Person | Status | Start Date | Due Date | Prioritization | Budget Allocated ($) | Actual Spend ($) | Notes/Comments
Week 1: Planning & Initial Setup
Week 1 | Review last month’s audit findings and action items | Jane Smith | In Progress | 2023-10-01 | 2023-10-05 | High | 500 |  | Critical for identifying recurring issues.
Week 1 | Gather departmental documentation and records | Mike Johnson | Not Started | 2023-10-02 | 2023-10-07 | High | 850.5 |  | Mandatory for compliance review.
Week 2: Data Collection & Verification
Week 2 | Verify data accuracy across finance, HR, and operations | Sarah Lee | Not Started | 2023-10-08 | 2023-10-14 | High | 675.75 |  | Data integrity check required.
Week 2 | Conduct internal walkthroughs with department leads | David Brown | Not Started | 2023-10-09 | 2023-10-15 | Medium | 450 |  | To ensure process alignment.
Week 3: Risk Assessment & Review
Week 3 | Perform risk assessment on high-impact areas | Jane Smith | Not Started | 2023-10-16 | 2023-10-23 | High | 750.95 |  | Focused on financial controls and compliance.
Week 4: Finalization & Reporting
Week 4 | Compile audit report and draft recommendations | Sarah Lee | Not Started | 2023-10-24 | 2023-10-31 | High | 950.5 |  | Mandatory delivery before month-end.
TOTAL BUDGET FOR MONTH: $4,177.70 | [6 empty] | Estimated Spend: $3,205.95 | Remaining Budget: $971.75