## Worksheet
Monthly Audit Preparation Planner
Week | Key Audit Activities | Status | Responsible Team/Person | Due Date | Notes/Comments
Week 1 (Mar 1–7) | Initial document collection and review | In Progress | Compliance Team | Mar 5, 2024 | Ensure all contracts and invoices are digitized.
| Set audit scope with internal stakeholders | In Progress | Audit Lead | Mar 6, 2024 | Confirm objectives and timeline.
| Create preliminary risk assessment matrix | In Progress | Risk Management | Mar 7, 2024 | Identify high-risk areas.
| Review prior audit findings and action items | In Progress | Audit Team | Mar 7, 2024 | Track resolution status.
Week 2 (Mar 8–14) | Conduct internal walkthroughs of key processes | Pending | Process Owners | Mar 12, 2024 | Schedule with department leads.
| Draft audit checklist per functional area | Pending | Audit Team | Mar 13, 2024 | Include key controls and evidence requirements.
| Review draft checklist with stakeholders | Pending | Audit Lead | Mar 14, 2024 | Gather feedback and finalize.
Week 3 (Mar 15–21) | Begin fieldwork: Testing of selected controls | Pending | Field Audit Team | Mar 18, 2024 | Focus on high-risk departments.
| Gather supporting documentation for key transactions | Pending | Data Analysts | Mar 20, 2024 | Verify accuracy and completeness.
| Update risk assessment based on field findings | Pending | Risk Management | Mar 21, 2024 | Revise matrix if needed.
Week 4 (Mar 22–31) | Finalize audit evidence collection | Pending | Audit Team | Mar 27, 2024 | Ensure all required samples are complete.
| Prepare draft audit report and recommendations | Pending | Audit Lead | Mar 29, 2024 | Incorporate feedback from team.
| Conduct draft report review meeting with management | Pending | Senior Leadership | Mar 30, 2024 | Schedule and distribute materials.
Total Items: |  |  |  |  | 12