## Worksheet
Audit Preparation - Monthly Planner Report Version
Task | Responsible Person | Due Date | Status | Progress (%) | Notes/Comments
Review previous month's audit findings | Jane Smith | 2024-04-05 | In Progress | 75% | Final review scheduled for April 3rd.
Compile financial statements | Mike Johnson | 2024-04-10 | Pending | 0% | Data collection in progress.
Update internal controls documentation | Sarah Lee | 2024-04-15 | Pending | 0% | To be reviewed by compliance team.
Conduct risk assessment meeting | David Brown | 2024-04-12 | Pending | 0% | Agenda drafted.
Schedule audit fieldwork dates | Lisa Wang | 2024-04-18 | Pending | 0% | Coordination with department heads.
Prepare audit checklist for Q2 | Tony Garcia | 2024-04-16 | In Progress | 50% | Initial version ready.
Send out pre-audit questionnaire | Elena Martinez | 2024-04-08 | Completed | 100% | All responses received.
Finalize audit plan and distribute | Jane Smith | 2024-04-25 | Pending | 0% | Review by management.