## Worksheet
Audit Preparation - Monthly Planner (Summary View)
Month | Task | Responsible Party | Status | Due Date | Completion %
January 2024 | Review financial statements | Finance Team | In Progress | 2024-01-15 | 65%
| Gather supporting documentation | Compliance Dept. | Pending | 2024-01-10 | 35%
| Internal review & validation | Audit Lead | Not Started | 2024-01-25 | 0%
February 2024 | Update risk assessment matrix | Risk Management | In Progress | 2024-02-18 | 75%
| Confirm audit scope with stakeholders | Audit Manager | Pending | 2024-02-12 | 15%
| Schedule audit team meetings | Project Coordinator | Not Started | 2024-02-28 | 0%
March 2024 | Finalize audit checklist | Audit Team | Not Started | 2024-03-10 | 0%
| Conduct preliminary walk-throughs | Audit Lead & Team | Not Started | 2024-03-15 | 0%
| Submit draft report to management | Audit Manager | Not Started | 2024-03-28 | 0%
Total Tasks: |  |  | 9 | Avg. Completion: 15% | Avg. Completion: 24%