## Worksheet
Audit Area | Objective | Review Status |  |  |  | Responsible Party | Due Date
|  | Documented? | Reviewed? | Tested? | Verified?
Section 1: Financial Controls
Revenue Recognition | Ensure revenue is recognized in accordance with GAAP and company policy | Yes | In Progress | No | No | Finance Team - John Smith | 2023-10-15
Accounts Payable Controls | Verify proper approval of vendor invoices and payment authorization processes | Yes | Yes | No | No | AP Manager - Lisa Chen | 2023-10-18
Section 2: Operational Processes
Inventory Management | Confirm accurate inventory counts and reconciliation procedures | Yes | In Progress | In Progress | No | Logistics Lead - Michael Brown | 2023-10-20
Procurement Approval Workflow | Validate that purchase requests follow proper escalation and authorization rules | Yes | Yes | No | No | Procurement Director - Sarah Johnson | 2023-10-17
Section 3: Compliance & Regulatory
Data Privacy (GDPR/CCPA) | Ensure personal data handling complies with applicable privacy regulations | Yes | In Progress | No | No | Compliance Officer - David Lee | 2023-10-22
Internal Audit Trail Review | Confirm audit logs are maintained and accessible for all critical systems | In Progress | No | No | No | IT Security - Emily Wang | 2023-10-25
Overall Status: |  |  | In Progress | No | No | Target Completion: 2023-10-30