## Worksheet
Audit Preparation - Planner Template
Task ID | Task Description | Responsible Party | Due Date | Status | Notes / Comments
T001 | Gather financial records for FY2023 | Finance Team | 2024-03-15 | Pending | Include all bank statements and invoices.
T002 | Review internal controls documentation | Compliance Officer | 2024-03-18 | In Progress | Verify completeness and accuracy.
T003 | Schedule audit meetings with department heads | Audit Coordinator | 2024-03-16 | Pending | Confirm availability via email.
T004 | Prepare audit checklist and templates | Audit Lead | 2024-03-17 | In Progress | Include risk assessment sections.
T005 | Conduct preliminary review of key processes | Process Analysts | 2024-03-19 | Pending | Focused on HR and procurement.
Audit Timeline Summary
Start Date:2024-03-10 |  | Planned End Date:2024-04-15 |  | Status:On Track