## Worksheet
AUDIT PREPARATION - DASHBOARD VIEW
PROJECT OVERVIEW
Project Name | Audit 2024 Q3 Review | Status | In Progress | Due Date | October 15, 2024
TASKS & PROGRESS
Task ID | Task Description | Responsible Team | Due Date | Status | Progress (%)
DOCUMENTATION & EVIDENCE COLLECTION
DOC-001 | Compile financial statements for Q3 2024 | Finance Department | Sept 30, 2024 | Completed | 100%
DOC-002 | Gather transaction records for key vendors | Procurement Team | Oct 3, 2024 | In Progress | 75%
DOC-003 | Collect HR compliance documentation | HR Department | Oct 5, 2024 | In Progress | 60%
DOC-004 | Verify asset register and depreciation records | IT & Finance Joint Team | Oct 10, 2024 | Delayed | 35%
REVIEW & APPROVAL PHASE
REV-001 | Internal review of financial data accuracy | Audit Committee | Oct 8, 2024 | In Progress | 50%
REV-002 | Management sign-off on audit findings draft | Executive Leadership | Oct 12, 2024 | In Progress | 40%
RISK & COMPLIANCE STATUS
Risk ID:RISK-01 | Outdated vendor contracts not updated in system | Severity | High | Mitigation Status | In Progress (Action Plan Initiated)
Risk ID:RISK-02 | Missing documentation for 3 recent approvals | Severity | Medium | Mitigation Status | In Progress (Pending Review)
SUMMARY METRICS
Total Tasks | 6 | Completed | 1 (17%) | In Progress | 4 (67%)
Delayed Tasks | 1 (17%) | Overall Status | On Track with Risks Identified
NEXT STEPS & ACTIONS
Next Action | Finalize documentation for audit submission by October 15; Schedule review meeting with external auditor.